## Sheet1
Requirements and Deliverables | [5 empty] | Requirements | % Done | Outstanding Hours To Complete
Task number | Requirement | Status | Comments | Deliver By | Effort | 19 | 5.263% | 104
2. User Acceptance, Feature Complete
2 | User acceptance, Feature Complete - All features demonstrated to user and are shown as complete on the TFS backlogs. - No missing features - User has access to candidate load and provided feedback | In Progress | We recently introduced more flows into the system. This poses a concern that not all features will be complete by the end of our sprints. | Sprint 4 | 3
3. Documentation
3.1 | User Documentation - Documentation on how to use the system is provided. This is an online documentation framework built into the application - Documentation must be in english and french. | New |  | Week 10 | 10
3.2 | Operational Documentation - Must provide documentation on how to install, uninstall, upgrade, etc. | New |  | Week 12 | 5
3.3 | Design Documentation - Documentation for design and maintenance teams that will inherit the production system and may need to do updates, enhancements or fixes - Includes diagrams, models, etc. | In Progress | We have all of our diagrams (use case, class, etc.) We just need to verify that we aren't missing anything | Week 12 | 2
4. Database
4.1 | Design and Implementation - Database is normalized and follows consistent naming standard | In Progress | It is normalized and follows consistent naming standards, but future model changes will happen to adhere to the new flows in the system | Sprint 4 | 4
4.1.1 | DB Logic - No business logic in stored procedures | Done | We do not use stored procedures and if we do, we have a business logic layer.
4.2.1 | Access From Application - The application authenticates into the production using IIS Application Pools. You can not have hard coded userId/Password details in your application web.config files. | In Progress | Currently working on implementing registering and login microsoft standards | Sprint 4 | 3
4.2.2 | Clara - The only access to Clara is via the Clara’s ReportClient views. No other access is provided in production. | In Progress | We have not connected to clara yet, but will use views. | Sprint 4 | 15
4.2.3 | External Reference - Access to external databases is via the MS SQL Server, Server Objects, Linked Server mechanism. Ideally, when migrating to production, a copy of the test database for your application will work by just changing the Linked Server setup. | New |  | Sprint 4 | 15
4.3 | Privacy Audit - Your application should only access data that is required for your application. An analysis must be done to deteremine if there is access to another personal data that is not required. | New |  | Sprint 4 | 2
4.4 | Deployment - Deployment documentation describing how the database will be deployed in production are covered in the Operational document (ref 3.2 Operational Documentation). - Deployment scripts are provided so that the operational team can install a fresh copy on any arbitrary MS SQL Server that meets the documented requirements. | New |  | Sprint 3 | 3
4.5 | Versioning - Consider that your database schema may change or have versions. How would the connecting application code know that it is communicating with a compatible version of the database? Some applications encode a version in the database and knows what backwardly compatible versions are supported. | In Progress | We have started implementing versioning but are not yet done | Sprint 3 | 2
4.5.1 | Upgrades/Migrations - If the schema changes, define the process of upgrading existing published databases. | New |  | Week 11 | 3
5. Application Code
5.1 | Design and Implementation (Application Code) - The design has been reviewed and approved by the team. At least two code inspections have occurred with forms returned to the Project Manager. (An early term and mid/late term review). | In Progress | We have done 1 code inspection so far. | Sprint 4 | 2
5.2 | Versioning - The application has a version number that is easily found by the user and is different for every build. The version number is a monotonically increasing function. The user will be able to report feedback based on the version number so given the version number. Ideally, given the version number, you should know what build, date, and source code version the application was built on. A suggested versioning scheme would be: x.y.z.b Where: x – Major version number y – Minor version number or Release number z – sprint number b – build number Hence you know 1.2.2.x would built as part of Release 2, sprint 2. | In Progress | We have started implementing versioning but are not yet done | Sprint 3 | 2
5.3 | Deployment - Deployment documentation describing how the application will be deployed in production are covered in the Operational document (ref 3.2 Operational Documentation). As we don’t have a build server environment, we will deploy/publish directly from Visual Studio. The documentation covers what will be required to deploy on any arbitrary server that meets the documented requirements. | New |  | Week 10 | 3
6. Testing
6.1 | System Testing - A System Test plan must be written by the Development Team and approved by the professor. System Test results and metrics are captured in a System Test report to show proof of testing and coverage. | New |  | Sprint 3 | 5
6.2 | Feature Testing - Feature testing is covered by individual Product Backlog Items (PBIs) that describe a feature or portions of the feature. The Development team is required to capture acceptance test cases and results for each PBI. | In Progress |  | Sprint 4 | 5
6.3 | Unit Testing - Unit test coverage reports are created by the Development Team which indicate how much of the code is tested. A Unit Test Report is provided to the Project Manager showing # tests, #run, # passed/failed, and overall % coverage. | In Progress |  | Sprint 4 | 20