## Sheet1
Requirements and Deliverables
Task Number | Requirement | Status | Comments | Deliver by | Effort
1 | User acceptance
1.1 | demonstate to the user all features in the backlogs on TFS | In progress | Unsure if we'll be able to complete everything since new tasks got added to TFS concerning the content specialist. | Sprint 4 | 3
1.2 | No features are missing
2 | Unit Testing | In progress |  | Sprint 4 | 16
2.1 | Get the unit test report from VS with all of our tests stats like number of tests run/passed/failed, and code coverage
3 | System Testing | New |  | Sprint 3 | 8
3.1 | Includes all results for tests in a report
3.2 | Needs to be approved by PM
4 | Feature Testing | In progress |  | Sprint 4 | 6
4.1 | Capture acceptance tests for PBIs on the product backlog
5 | Database | In progress |  | Sprint 4
5.1 | Normalize and make sure it follows our team's standards | In progress |  |  | 5
5.2 | Make sure that there's no logic in the DB | Done |  |  | 0
5.3 | Accessed using IIS application pools | New | Changing our system right now to adhere to the MS standards |  | 20
5.4 | Access Clara through ReportClient views | New | Currently not connecting to Clara at all, but this will be our method if/when that gets implemented |  | 15
5.5 | Make sure that the DB only stored necessary personal information for privacy concerns | New |  |  | 4
5.6 | Create deployment scripts for the DB | New |  | Sprint 3 | 2
5.7 | Make sure the DB is versioned for compatilibity with different releases of the application - makes sure they aren't too tightly coupled | In progress |  |  | 5
6 | Operational Documentations | New |  | Week 12 | 7
6.1 | Provide docs on how to manage the software (install, upgrade, etc)
7 | Design Documentation | In progress |  | Week 12 | 4
7.1 | Add models and diagrams
7.2 | Add documentation for future maintenance teams
8 | User Documentation | New |  | Week 10 | 12
8.1 | Bilingual documentation
8.2 | Documentation built into the system to teach a user how to use the system
9 | Application Code
9.1 | Make a standardized way of versioning the system: major.minor.sprint.build ex: 2.2.4.x would be version 2 (because RAC already exists), release 2, sprint 4, build number x. | In Progress |  | Sprint 3 | 5
9.2 | Code inspections and code base and architecture of whole system approved by the team | In Progress |  | Sprint 4 | 2
9.3 | Deploying the application through VS since we don't have access to the actual deployment environment. There will be documentation for this stating server requirements and other information in the operational documentation. | New |  | Week 10 | 7
| Requirements: | Done: | Remaining hours
| 21 | 4.7% | 121